EQUESTRIA GIRLS – SCRIPT SCHEDULE

DVD4 script start 11/17 (17 week schedule including xmas/ny)

EG Special #1 script start 11/24 (14 week schedule including xmas/ny)

EG Special #2 script start 12/1 (14 week schedule including xmas/ny)

Take a look at the schedules below & let us know if anyone has any questions or issues with these.  Please note the approval times are all in — meaning I’ve left a week where possible in case you’re planning multiple passes (studio then brand etc), but they’ll all have to fit into these times.

| EGDVD4 |  |  |  |
| --- | --- | --- | --- |
| Start Premise | 11/17/14 |  |  |
| Premise due | 12/1/14 |  | 2 weeks |
| Notes due | 12/8/14 |  | 1 week |
| Outline due | 12/22/14 |  | 2 weeks |
| Notes due | 1/12/15 |  | 1 week plus 1 week xmas break |
| 1st due | 2/2/15 |  | 3 weeks |
| Notes due | 2/9/15 |  | 1 week |
| 2nd due | 2/23/15 |  | 2 weeks |
| Notes due | 2/27/15 |  | 3 days |
| Polish due | 3/6/15 |  | 1 week |
| Notes due | 3/10/15 |  | 3 days |
| Final Lock (and last tweaks | 3/13/15 |  | 3 days |
| EG SPECIAL #1 |  |  |  |
| Start Premise | 11/24/14 |  |  |
| Premise due | 12/1/14 |  | 1 week |
| Notes due | 12/8/14 |  | 1 week |
| Outline due | 12/22/14 |  | 2 weeks |
| Notes due | 1/5/15 |  | 1 week plus 1 week xmas break |
| 1st due | 1/26/15 |  | 3 weeks |
| Notes due | 2/2/15 |  | 1 week |
| 2nd due | 2/9/15 |  | 1 weeks |
| Notes due | 2/13/15 |  | 3 days |
| Polish due | 2/18/15 |  | 3 days |
| Notes due | 2/23/15 |  | 3 days |
| Final Lock (and last tweaks | 2/26/15 |  | 3 days |
| EG SPECIAL #2 |  |  |  |
| Start Premise | 12/1/14 |  |  |
| Premise due | 12/8/14 |  | 1 week |
| Notes due | 12/15/14 |  | 1 week |
| Outline due | 1/5/15 |  | 2 weeks plus 1 week xmas break |
| Notes due | 1/12/15 |  | 1 week plus 1 week xmas break |
| 1st due | 2/2/15 |  | 3 weeks |
| Notes due | 2/9/15 |  | 1 week |
| 2nd due | 2/16/15 |  | 1 weeks |
| Notes due | 2/20/15 |  | 3 days |
| Polish due | 2/25/15 |  | 3 days |
| Notes due | 3/2/15 |  | 3 days |
| Final Lock (and last tweaks | 3/5/15 |  | 3 days |

EG SPECIAL #3

Start - 6/1/15

Outline Due – 6/29/15

First Draft Due – 7/27/15

Second Draft Due – 8/10/15

Final Draft Due – 8/24/15